## PID
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Patient Recruited? | Date of First Patient Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Patient Recruited | Duration between Date Site Selected and First Patient Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to:
163224 | 19/YH/0409 | 269176 | Function REplacement in repeated Self-Harm: Standardising Therapeutic Assessment and the Related Therapy - WP3 - Feasibility (FReSH START) | No |  | 22 |  |  | 2019-12-02 | 2020-02-13 | 2020-02-07 | 2020-02-20 | 2020-03-06 |  | 2020-03-09 | J - Other | Recruitment put on hold then study closed due to COVID-19 | Neither
163225 | 19/LO/1667 | 271363 | Clinical and cost-effectiveness of a New psychological intervention to support Independence in Dementia (NIDUS) for family carers and people living with dementia in their own homes: A randomised controlled trial | Yes |  | 13 | 26 | 39 | 2020-06-02 | 2020-06-18 | 2020-01-13 | 2020-06-18 | 2020-07-01 |  | 2020-07-07
Note on A1: System generated field
Note on F1: Format dd/mm/yyyy. Only available if First Patient Recruited = “Yes”
Note on G1: System generated field. Please check your dates if value is negative.
Note on H1: System generated field. Please check your dates if value is negative.
Note on I1: System generated field. Please check your dates if value is negative.
Note on R1: Please use the free text comment box for more information about the trial. Character limit: 500

## Sheet1
Options for reasons for delay
A - Permissions delayed/denied
B - Suspended by sponsor
C - Closed by sponsor
D - Sponsor Delays
E - Staff availability issues
F - No patients seen
G - No patients consented
H - Contracting delays
I - Rare diseases
J - Other
K - Not Used
L - Not Used
M - Not Used
N - Not Used
O - Not Used