## PID
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Patient Recruited? | Date of First Patient Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Patient Recruited | Duration between Date Site Selected and First Patient Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to:
159452 | 17/LO/0596 | 220840 | A randomised controlled trial comparing supported Mindfulness-Based Cognitive Therapy self-help to supported Cognitive Behaviour Therapy self-help for adults experiencing depression | Yes | 2019-05-16 | 12 | 30 | 42 | 2019-03-05 | 2019-04-04 | 2017-07-13 | 2019-04-04 | 2019-04-16 |  | 2019-04-16
159453 | 19/LO/0088 | 257667 | A randomised controlled trial of a structured intervention for expanding social networks in psychosis (SCENE) | Yes | 2019-06-26 | 13 | 9 | 22 | 2019-04-12 | 2019-06-04 | 2019-01-24 | 2019-06-04 | 2019-06-17 |  | 2019-06-26
159454 | 19/YH/0237 | 259335 | Feasibility study of Telemedicine in Addictions Randomised Controlled Trial | Yes | 2019-09-24 | 96 | 0 | 96 | 2019-06-20 | 2019-06-20 | 2019-08-27 | 2019-09-23 | 2019-09-24 |  | 2019-09-24 | A - Permissions delayed/denied | Delay in gaining HRA approval led to us not being able to sign contracts and then initiate the study | Neither
159455 | 18/WA/0209 | 238724 | Problem Adaptation Therapy for individuals with mild to moderate dementia and depression. The PATHFINDER Trial. | Yes | 2019-09-24 | 27 | 28 | 55 | 2019-05-02 | 2019-07-31 | 2018-06-25 | 2019-08-27 | 2019-08-27 |  | 2019-09-17
159456 | 19/YH/0409 | 269176 | Function REplacement in repeated Self-Harm: Standardising Therapeutic Assessment and the Related Therapy - WP3 - Feasibility (FReSH START) | No |  | 22 |  |  | 2019-12-02 | 2020-02-13 | 2020-02-07 | 2020-02-20 | 2020-03-06 |  | 2020-03-09 | J - Other | Recruitment put on hold due to COVID-19 | Neither
Note on A1: System generated field
Note on F1: Format dd/mm/yyyy. Only available if First Patient Recruited = “Yes”
Note on G1: System generated field. Please check your dates if value is negative.
Note on H1: System generated field. Please check your dates if value is negative.
Note on I1: System generated field. Please check your dates if value is negative.
Note on R1: Please use the free text comment box for more information about the trial. Character limit: 500

## Sheet1
Options for reasons for delay
A - Permissions delayed/denied
B - Suspended by sponsor
C - Closed by sponsor
D - Sponsor Delays
E - Staff availability issues
F - No patients seen
G - No patients consented
H - Contracting delays
I - Rare diseases
J - Other
K - Not Used
L - Not Used
M - Not Used
N - Not Used
O - Not Used